## Table 1
Great-West Life Information Services
Investment Accounting System (IAS) - Segregated Funds Financial Services (SFFS) Test Strategy
Version 1.3 March 26, 2014
Confidential Multicompany, 2020 Page 1
Document Revision History
Document Location: \\Gwlanfs8\ias program\Testing\Establish Test Strategy and Plan
Version | Date | Author/Editor | Comments
0.1 | February 28, 2013 | Larry Folmes | Initial version of this document.
0.2 | March 19, 2013 | Larry Folmes | Feedback from D. Emek & J. Bettencourt
1 | March 26, 2013 | Larry Folmes | Feedback from General Review
1.1 | June 28, 2013 | Larry Folmes | Updated to align to revised Project Plan
1.2 | February 12, 2014 | Larry Folmes | Updated to reflect the revised Testing Scope and Project Plan
1.3 | March 26, 2013 | Larry Folmes | Feedback from General Review and revised project schedule
 2003 by GLI, Canada All rights reserved. No part of this publication may be reproduced or transmitted in any form or by any means, electronic or mechanical including photography, recording or any information storage or retrieval system without permission in writing from the publisher. Printed in Canada Template Version: 1.1.1 Template Name: Test Strategy-V1.0 Template Version Date (mm/dd/yy): 10/18/07

## Table 2
Table of Contents TABLE OF CONTENTS 3 1 INTRODUCTION 4 1.1 PURPOSE 4 1.2 PROJECT CONTEXT AND BACKGROUND 4 1.3 SCOPE 5 1.4 DOCUMENT TERMINOLOGY AND ACRONYMS 10 1.5 REFERENCES 10 1.6 TEST OBJECTIVES 11 1.7 TEST MOTIVATORS 11 2 TEST APPROACH 12 2.1 STANDARD QUALITY PROCEDURES & GUIDELINES 12 2.2 CONDUCTING TESTS 12 2.2.1 Unit Testing 12 2.2.2 Functional Testing 12 2.2.3 System Integration Test 12 2.2.4 Regression Testing 13 2.2.5 End-to-End System Testing (Cycle Test) 13 2.2.6 Parallel Testing (Model Office) 13 2.2.7 User Acceptance Testing 14 2.2.8 Security Testing 14 2.3 TEST DELIVERABLES - SFFS 14 2.4 HIGH LEVEL TEST SCHEDULE 15 3 ENVIRONMENTAL NEEDS 17 3.1 BASE SYSTEM HARDWARE 17 3.2 BASE SYSTEM SOFTWARE 17 3.3 TEST ENVIRONMENT CONFIGURATION 18 3.4 TOOLS 18 4 BUSINESS ACCEPTANCE CRITERIA 19 4.1 ACCEPTANCE TEST STRATEGY 19 5 RISKS, DEPENDENCIES, ASSUMPTIONS, AND CONSTRAINTS 20
5.1 | RISKS | 20
5.2 | DEPENDENCIES | 20
5.3 | ASSUMPTIONS | 20
5.4 | CONSTRAINTS | 21
6 SIGN-OFF – VERSION 1.3 22 APPENDIX A: TESTING CHECKLISTS 24

## Table 3
1 Introduction 1.1 Purpose The purpose of the Test Strategy document for the Investment Accounting System (IAS) Program - SFFS is:  To define a Test Strategy that will guide the project’s testing deliverables through to completion of the SFFS implementation in 2014.  To outline the testing approach, test objectives, scope and the different types of test execution phases that will be used.  To identify the target test items, test environments, test tools, test case structure and defect management process.  To build a common understanding and agreement amongst testing participants and approval from stakeholders.  To ensure that all functionality and changes introduced into the system are compliant and accurate based on the Business requirements and system specifications 1.2 Project Context and Background MPower, an investment accounting system provided by CGI, is currently used by the GWL segregated fund and general fund back offices; and IG and Mackenzie mutual fund back offices (the “Stakeholders”). The MPower replacement project became a requirement when CGI indicated that they will soon phase out MPower in favor of their new product – Mvest. The change from MPower to MVest is viewed by the Stakeholders to be so significant that it is a system replacement, not simply a system upgrade. Since the Stakeholders are faced with a mandatory system replacement, they have taken the opportunity to evaluate multiple investment accounting system vendors to see which system will best meet the needs of our organization. There was a desire by all Stakeholders to identify a single solution that met all Stakeholders’ needs and provided the best solution from a Power Financial Corp. standpoint. The Stakeholders have undertaken a formal and rigorous process to identify the replacement system that best meets their business needs from a strategic, financial, operational and technological perspective. After an extensive and rigorous process which included RFI and RFP stages, a period of test driving the potential systems, performance tests by vendors and information obtained from industry consultants, GWL identified Multifonds (MF) as the vendor with the best fit for the GWL segregated fund and general account back offices and launched a Concept of Operations as the final round of diligence before requesting and obtaining C-Level approval to proceed with the implementation of a new Investment Accounting System. The Investment Accounting System (IAS) program – SFFS Business Unit implementation will include the following projects:  Core product implementation  Integration – Core Product |  Infrast ructur e  IRFI Gap Closur e The IAS Core Implementatio n Project for SFFS is responsible for functionally configuring the Multifonds Fund Accounting application, converting data from the legacy systems (MPower5 and SF01) into the Multifonds system, decommissioni ng the legacy systems and transitioning the business from legacy processes to the future- state processes. The IAS Integration Project is responsible for replacing existing interfaces from MPower5 and SF01 to the new Multifonds solution and, where required, developing new interfaces. Some current interfaces may no longer be required and there may
become a need for transitional interfaces required only in the short-term to support successful implementation of the Multifonds solution. The Investment Accounting System (IAS) Infrastructure Project is responsible for putting in place the hardware, software, storage and network components that will support the new IAS solution. It is also responsible for preparing the IS organization to support the new solution and successfully transitioning the infrastructure to production and maintaining that infrastructure until the close-out of the IAS Program at which time it will be transitioned to business as usual (BAU). The IAS IRFI Gap Closure Project is responsible for filling any gap created as a result of the decommissioning of the SF01 System. 1.3 Scope
There will be three testing phases for the Investment Accounting System (IAS) – SFFS. The following initiatives will be part of the testing effort for each testing phase:  Phase 1 – Configuration o Infrastructure Testing – Non-Production Environments  Configuration testing of the new Non-production environments by the Infrastructure Team will include:  Hardware  Operating System  Database  Network  Authorization  Authentication  Security Testing  Infrastructure Vulnerability Assessment Scan o Multifonds Fund Accounting – Release 4.0 Configuration  System Configuration  System Configuration/Setup will be created by the vendor in conjunction with the Business for the following: o Accounting Charts o Security Types (GTI’s) o Operation Codes o NAV Codes o Fee Codes o Currency Codes o Industry Codes o Tax Tables o Valuation Model o Country Codes
Monitor (WEM set up)  Application Parameters  Setup validation  Security Groups o Multifonds Fund Accounting – Release 4.0 Configuration Functional  Transaction focused testing of all security types to validate the system configuration meets the Business requirements  Security Testing  Application Vulnerability Assessment Scan  Phase 2 – Functional Core/Gap Closure o Multifonds Fund Accounting – Release 4.1 – Functional Gaps  GWL Functional Gaps  DEV40 - Mutual Fund Trading  DEV63 - Asset Allocation Processing  DEV56 - Peer Groups Exception Management  DEV23 - Fund of Fund Rate of Return Analysis  DEV65 – Automated Distribution Reinvestment  DEV64 - Daily Payable Expense  DEV68 – WEM Control – Identify Deleted NAV Confirmations  DEV51 - User Defined Fields and User Defined Comments  DEV09 - Multi-book Accounting  DEV62 – Fund ROR and Starting Unit Value  DEV48 - Rating Agency Management  DEV72 - Check on Duplicate Trades  DEV71 - Control on Closed Series  DEV70 – Control on Large Security or Shareholder Transaction  DEV69 – NAV Reporting o Multifonds Fund Accounting - Release 4.1 – Security Pricing & WEM  Security Pricing  Inject Price Files  Price Scrubbing / Levels  Foreign Fair Value  Market Value Validation  Price Rollover  WEM – Workflow Exception Management  WEM Configuration  Test WEM Controls  WEM HSM o Multifonds Fund Accounting – Release 4.1 – NAV Cycle  Full Functional test of the NAV Cycle  Start of Day (SOD)  Final (FNL)
nce testing of the Multifonds Fund Accounting application running on the GWL environments is required  Phase 3 – Integration/Reports/Migration/Model Office o Integration Testing – Functional  SFFS Interfaces  Test planning/execution of SFFS interfaces throughout the agile development cycle  Demand Service - TBD o Security Request Process  Security Master Info  XIP FO to: SS&CNet, Expertus, Solium

## Table 4
 Inbound o Market Data (Pricing)  Pre NAV/PU End of Day Process  Security Prices  Foreign Exchange Rates  Dividend Announcement s
o SS&CNet  Trade Capture Process  Trade Info
o Expertus  Trade Capture Process  Trade Info
o Solium  Trade Capture Process (Possible Manual Load – TBD)  Trade Info
o XIP FO  Trade Capture Process  Trade Info  Security Master Info
o CTI |  Pre NAV/PU End of Day Process  Transactions
o MLS  Pre NAV/PU End of Day Process  Transactions
o Optimus  Pre NAV/PU End of Day Process  Transactions
o FundServ
y Process  Transactions
o InfoBase  Post NAV/PU End of Day Process  Security Positions  GL Balances  Security Master info  Transactions – Security Trades  Fund/Series Values  Security Prices
o XIP FO  Start of Day Process  Security Positions  GL Balances (includes Cash)
o IC – FO  Start of Day Process  Security Positions  GL Balances o SS&C Recon (BO and FO)  Start of Day Process  Security Positions  GL Balances – Cash Positions
o GRDB  Post NAV/PU End of Day Process  Security Positions  Security Master info
o Solium  Post NAV/PU End of Day Process (May NOT be required TBD)  Security Positions o SS&C Recon (BO and Custodian)  Post NAV/PU End of Day Process  Security Positions  GL Balances – Cash Positions  Cash Transactions o Internal/External Parties  Post NAV/PU End of Day Process  Fund/Series Values
ces with downstream systems o I  Inbound n o Deposits /Withdrawals Process f  Transactions r  Outbound a o NAV End of Day Process s (Valuation after t Deposits/Withdrawals) r  Fund/Series Values u o Post NAV/PU End of Day c Process (Valuation before t Deposits/Withdrawals) u  Fund/Series Values e o IRFI Functional Enhancements T e  IRFI Functional Enhancements are required due s to the decommissioning of the SF01 system t  New IRFI tables/processes to support the move i of data/functionality from SF01 to IRFI n  All IRFI processes that access the new IRFI g tables for the SF01 data  New functionality to assume SF01 processing – – TBD – Scope to be confirmed during Requirements/Analysis phase P  Forcing of unit values including r maintaining a category force indicator o  London Life zero tax factors d  Future valuation dates u c t o InfoCentre SFFS i  GWL developed InfoCentre SFFS o Reports/Extracts/Views n E o Data Migration/Conversion n  Test the migration and reconciliation of funds i including all hierarchical dependencies. Start by o migrating simple funds, moving to larger scale n funds; investigating/fixing/improving from one m run to another until a full volume test is e achieved. n t o Cycle Test – Functional Integration Test  Cycle Test Detail Test Planning  Functional/Integration testing of all inbound and outbound SFFS interfaces  Data Flow and Data Integrity test from Source Systems, Core and Downstream systems  Validate the correct interfaces are created with the correct data content for each of the 3 daily NAV cycles  Validation of the interfaces files by the Downstream systems

## Table 5
Note: | testing of the new Production environment by the Infrastructure Team will include:  Hardware  Operating System  Database  Network  Authorization  Authentication  Disaster Recovery (DR) Test  Security Testing  Infrastructure Vulnerability Assessment Scan o Model Office  Parallel Test – Scope TBD during detail test planning  Performance Timing Tests  Load of D/W’s from IRFI  Processing of Available Cash for DEV40 trades (FundSERV, ASL, MSL)  End of Day (EOD) NAV including end to end WEM  Final Security Testing  Infrastructure and Application Vulnerability Assessment Scan | 1.5 Refer ence s The following is a list of deliverables that will be used as input or otherwise referenced in the development of this document. Project Documents:  Invest ment Accou nting Syste m (IAS) Progra m – Testin
 Scope items may change during the year due to Business and Project priorities. 1.4 Document Terminology and Acronyms The following is a list of acronyms used in this document:  AD – Application Delivery  BA – Business Analyst  BAU – Business As Usual  BRD – Business Requirements Document  ETL – Extract, Transform and Load  FIT – Functional Integration Testing  GRDB – Global Reporting DataBase  IAS – Investment Accounting System  PM – Project Manager  QA – Quality Assurance  SAN – Systems Analyst  SD - Software Developer  SFFS - Segregated Funds Financial Services  TAS – Tax Allocation System  UAT – User Acceptance Testing |  |  | g Frame work: \\Gwla nfs8\ias program\Testi ng\Establish Test Strategy and Plan  Invest ment Accou nting Syste m (IAS) Progra m – Stand ard Qualit y Proce dures & Guidel ines:

## Table 6
Test Level
Parallel Test (Model Office)
Acceptance Test
Security Testing
\\Gwlanfs8\ias program\Testing\Establish Test Strategy and Plan  All RFP Business Requirements Documents are located within the following Folder: \\Gwlanfs8\ias program\99 RFP Work Stream\RFP Business Requirements Analysis and High Level Design  All Gap BRD are located on the SharePoint Site - SEG-Net :  All Integration Requirements Documents are located within the following Folder:
\\Gwlanfs8\ias program\30 Integration Project\30.2 Integration Blueprint 1.6 Test Objectives The general objective of testing is to verify that the system solution meets the stated Business requirements. The specific objectives for each test level are defined below: |  |  | 1.7 Test Motiv ators Validate all functionality and functional enhancements introduced in the new application work correctly according to the Business Requirements and System Specifications. Validate all interfaces/data feeds, user interfaces and ETL processes work correctly and deliver the expected results. Obtain Business Acceptance of the delivered functionality.
Test Level | Responsibility | Objective
Unit Test | Development Teams / Vendor |  To verify each software unit executes according to design specifications, and that it is free of data and logic errors.
Functional Test | Test Team |  To verify the Multifonds Fund Accounting Core Product, Configuration setup/changes, gap closure enhancements, data migration and reports work and process correctly according to Business Requirements.
System Integration | Test Team |  To verify all system interfaces in the system specifications process correctly with the new application and existing applications  To verify that interdependent modules/systems processes work correctly together after the inclusion of the new application and modified code.
Regression Test | Test Team |  To verify the existing code continues to process correctly after the integration of the modified code.  Test Team will determine the extent of regression testing to be performed by analyzing the impact the functional change has on the system.
Non-Functional Test | IS Technical Test Team |  Run automated performance scripts to verify the new application meets the performance requirements.
End-to-End System Test (Cycle Test) | Test Team |  To verify all system changes, system interfaces and data feeds work correctly together and deliver the expected results.

## Table 7
Technique Objective: | To sp
2 Test Approach
Technique Objective: | To verify the Multifonds Fund Accounting Core Product, configuration setup/changes, gap closure enhancements, data migration and reports work and process correctly according to Business Requirements.
Technique/Strategy: | The QA test team from the Core Implementation project will functionally test the application & code changes for the Core Product, configuration setup/changes, gap closure enhancements, data migration and reports in the GWL test environments. The QA test team from the IRFI Gap Closure project will functionally test the IRFI application & code changes required to fill the gap created by the decommissioning of the SF01 system. Detail Test Plan (s) will contain all planned and reviewed test scenarios and test cases that will be executed for each testing phase.
Required Tools: | ClearQuest will be used as the defect management tool for all systems. Any results which vary from the expected result will be logged as a defect.
Success Criteria: | Successful completion of all planned test cases with no outstanding Severity 1 or 2 defects.
Special Considerations:
2.1 Standard Quality Procedures & Guidelines The test effort for all three phases of the Investment Accounting System (IAS) Program – SFFS Business Unit implementation will follow the QA procedures as outlined in the Investment Account System (IAS) Program Standard Quality Procedures & Guidelines: IAS Program |  | Technique/Strategy: |  | Th m Th en re
Required Tools:
|  | Success Criteria: |  | N ex in
Special Considerations:
Standard Test Proced
2.2 Conducting Tests 2.2.1 Unit Testing |  |  | 2.2.2 Funct ional Testi ng 2.2.3 Syste m
Technique Objective: | To validate that each software module executes according to design specifications and is free of any logic defects.

## Table 8
Integration Test |  | 2.2.5 End- to- End Syste m Testi ng (Cycl e Test)
Technique Objective: | To verify all system interfaces in the system specifications process correctly with the new application and existing applications To verify that interdependent modules/systems processes work correctly together after the inclusion of the new application and modified code.
Technique/Strategy: | The QA test team from the Integration project will functionally test all new interfaces from/to the Core Product and validate the data flow from/to the existing applications in the GWL test environments.
Required Tools: | ClearQuest will be used as the defect management tool for all systems. An results which vary from the expected result will be logged as a defect. |  | y Technique Objective: |  | T to
Success Criteria: | Successful completion of all planned test cases with no outstanding Severit or 2 defects.
|  |  | Technique/Strategy: |  | A pr to w int ap T In th
Special Considerations:
2.2.4 Regression Testing
Technique Objective: | To verify the existing code continues to process correctly after the integratio of the modified code. |  | Required Tools: |  | Cl re
|  |  | Success Criteria: |  | S or
Technique/Strategy: | Regression testing will be combined with the functional/integration testing performed by the QA Test Team (s).
Special Considerations:
| The QA Test Team (s) will determine the extent of regression testing to be performed by analyzing the impact of the functional change to ensure the existing code (after the integration of the modified code) continues to work correctly and deliver the expected results. The analysis of the impact of the functional change will include the SAN, SD and BA if required. |  |  | 2.2.6 Paral lel Testi ng (Mod el Offic e)
Required Tools: | ClearQuest will be used as the defect management tool for all systems. Any results which vary from the expected result will be logged as a defect.
Success Criteria: | Successful completion of all planned test cases with No outstanding Severity 1 or 2 defects.
Special Considerations:
|  |  | Technique Objective: |  | T sa re
o
h
u
o

## Table 9
Technique Objective: | To verify the processing of a number of business process cycles using the same sub-set of data on both the new and old systems; produce the same results. | Technique Objective: |  | To inf of
Technique/Strategy: | A series of Business process cycles will be executed on the same subset of data on both the new and old systems. Test results will be validated on both the new and old systems to verify the same results are obtained. | Technique/Strategy: |  | Te as th hi ap re
Required Tools: | ClearQuest will be used as the defect management tool for all systems. Any results which vary from the expected result will be logged as a defect.
Success Criteria: | Successful completion of all planned test cases with No outstanding Severit or 2 defects.
|  | Required Tools: |  | Te
Special Considerations: |  | Success Criteria: |  | O
Special Considerations:
2.2.7 User Acceptance Testing
Technique Objective: | To establish business acceptance of the solution and verify the solution works correctly and delivers the expected results from the business perspective.
Technique/Strategy: | User Acceptance Testing (UAT) will be performed by the Business. The Business will review and approve all the completed detail test plans and test results from all the functional and system integration testing performed through the three phases of the SFFS implementation. The End-to-End and Parallel testing will be the final part of the User Acceptance Testing. End-to-End and Parallel (UAT) test plans will be created/executed by the Business and contain all the test scenarios/cases (test sets/conditions) required to be executed successfully to obtain business acceptance.
Required Tools: | ClearQuest will be used as the defect management tool for all systems. Any results which vary from the expected result will be logged as a defect.
Success Criteria: | Successful completion of all the End-to-End (UAT) planned test cases and approval of all functional and system integration completed test plans and test results.
Special Considerations:
2.2.8 Security Testing |  |  | 2.3 Test Deliv erabl es - SFFS  This is a
Technique Objective: | To verify there are no critical security vulnerabilities with either the infrastructure assets and/or the application that could compromise the integrity of business processes or allow unauthorized access to secure sensitive data.

## Table 10
Canada Life Internal Information and should not be shared outside.  Test Strategy - SFFS  Test Deliverables by Test Phase o Detailed Test Plan (s) – Test Scenarios/Cases (Test Sets/Conditions) o Test Managements Reports  Weekly Dashboard/Status Report  Defect Reports o Completed Detailed Test Plan (s) and Test Results o Test Summary Report |  |  |  |  | System (IAS) Program – SFFS Implementatio n – Mar 2013 – May 2014.
Test Activity |  | Mar |  | Apr
Test Strategy - SFFS |  | TBD
Phase 1 - Infrastructure
Phase 1 – MF Rel 4.0 – Configuration Test Plan
Phase 1 – MF Rel 4.0 – configuration Test Execution
Phase 1 – MF Rel 4.0 – Functional Test Planning
Phase 1 – MF Rel 4.0 – Functional Test Execution
Phase 2 – Rel 4.1 – Dev Test Planning
Phase 2 – Rel 4.1 – Dev Test Execution
Phase 2 – Rel 4.1 – Pricing & WEM Test Planning
Phase 2 – Rel 4.1 – Pricing & WEM Test Execution
Phase 2 – Rel 4.1 – NAV Cycle Test Planning
Phase 2 – Rel 4.1 – NAV Cycle Test Execution
Phase 3 – Integration – Testing throughout Agile Development & FIT
IRFI System Testing
IRFI Integration Testing
IRFI UAT/End-User Testing
IRFI Implementation
Info Center Reporting
Phase 3 – Data Migration – Test Planning
Phase 3 – Data Migration – Test Execution
Cycle Test – Test Planning
SFFS Test Strategy
Test Phase 1- Configuration
Detail Test Plan (s)
Test Execution (s) – Status / Defect Reports
Completed Detail Test Plan (s) & Results
Phase 1 Test Summary
Test Phase 2 – Functional Core/Gap Closure
Detail Test Plan (s)
Test Execution (s) – Status / Defect Reports
Completed Detail Test Plan (s) & Results
Phase 2 Test Summary
Test Phase 3 – Integration/Reports/ Migration/Model Office
Detail Test Plan (s)
Test Execution (s) – Status / Defect Reports
Completed Detail Test Plan (s) & Results
Phase 3 Test Summary
2.4 High Level Test Schedule
Below is the high-level test schedule for the Investment Accounting

## Table 11
Cycle Test – Test Execution | TBD | TBD | TBD
Phase 3 – Model Office – Test Planning |  | TBD | TBD
Infrastructure Testing - Prod |  | TBD | TBD
Phase 3 – Model Office – Test Execution |  |  | TBD | TBD
Implementation –SFFS |  |  |  | TBD

## Table 12
System
Resource | Qu
Integration Server
Application/Database Servers
Storage
Central File Share Server
SQL Transition DB Server
SQL WEB Server Tool
MOVEIT Central Server
MOVEIT DMZ
3 Environmental Needs 3.1 Base System Hardware The following table sets forth the system resources for the test effort.
System Resources
Resource | Quantity | Name and Type
Presentation Layer Server | 1 | - GWIASAPU1 (Dev, FIT, UAT & Support) - IBM x3650 M4, 3.46Ghz, dual sockets, single 8 Core CPU - Memory: 96GB - Disk: 146 GB mirrored
Reporting Server | 1 | - GWIASAPU2 (Dev, FIT, UAT & Support) - IBM x3650 M4, 3.46Ghz, dual sockets, single 8 Core CPU - Memory: 96GB - Disk: 146 GB
Presentation Layer Server | 1 | - GWIASAPP1 (Prod) - IBM x3650 M4, 3.46Ghz, dual sockets, single 8 Core CPU - Memory: 96GB - Disk: 146 GB mirrored
Presentation Layer Server | 1 | - GWIASAPP2 (Prod) - IBM x3650 M4, 3.46Ghz, dual sockets, single 8 Core CPU - Memory: 96GB - Disk: 146 GB mirrored
Reporting Server | 1 | - GWIASAPP3 (Prod) - IBM x3650 M4, 3.46Ghz, dual sockets, single 8 Core CPU - Memory: 96GB - Disk: 146 GB
Reporting Server | 1 | - GWIASAPP4 (Prod) - IBM x3650 M4,
3.2 Base Syste m Soft ware The following base software elements are

## Table 13
required in the test environment for this Test Strategy. |  |  | 3.3 Test Envir onme nt Confi gurat ion The following Test Environment Configurations needs to be provided and supported for this project.  DEV – Development (DEV1, DEV2)  FIT – Integration (FIT1)  UAT – User Acceptance (UAT1, UAT2, UAT3, UAT4) 3.4 Tools
Software Element Name | Version | Type and Other Notes
Client Tier
Internet Explorer | 7 or 8
Windows | 7
Java applet | SUN JRE 1.6.0_20
Middle Tier – Presentation Server
Windows Server | 2008 R2
Weblogic Suite | 2010-03-05
Middle Tier – Reporting Server
Business Intelligence Publisher
Weblogic Server Enterprise Edition
Middle Tier – Integration Server
Ab Initio Co>Operating System | 3.0.4
Database Server
Oracle Server Database Enterprise Ed | 11g R2 11.2.0.3
Oracle Diagnostics Pack
Oracle Partitioning
Multifonds | 4
Backup Software (UNIX & Windows) |  | Networker
Networker Backup Agents |  | 25 Pack Networker licenses for Windows and UNIX
The following tools will be used for this project
Defect Tracking
Project Management
4 Business Acceptance Criteria 4.1 Acceptance Test Strategy
The successful execution of the different levels of testing for each test phase will prove that the application can be deployed to Production. UAT (User Acceptance testing) will establish business acceptance of the application and verify the application works correctly and delivers the expected results from the Business perspective. The Business will review and approve the all detailed test plans and test results obtained during the different levels of testing performed by the test team (s) for all three phases. The Model Office Testing will consist of the End-to-End and Parallel Testing. The Model Office testing will be the final part of the User Acceptance Testing. End-to-End and Parallel (UAT) test plans will be created/executed by the Business and contain all the test scenarios/cases (test sets/conditions) needed to be executed to successfully to obtain business acceptance.

## Table 14
5 Risks, Dependencies, Assumptions, and Constraints 5.1 Risks All project risks are documented and managed at a project/program level. The following risks associated with testing should also be highlighted: | [6 empty] | Dependency between
dependent on requirements/specifications being completed on time.
Test execution is dependent on code being written/modified and unit tested by GWL and the vendor respectively
Test execution schedule is based on the vendor’s software release schedule
Risk |  | Probability |  | Impact | Mitigation Strategy | Contingency
Risk that testing resources are not 100% allocated to the projects will impact project schedule |  | H |  | H | Full time resources internal/external can be requested. Monitor shared resources workload against schedule. | Additional external resources can be engaged to meet project timelines.
5.3 Assu mpti ons
Risk that delays encountered in the testing phase of one project may impact the testing schedule of the other projects |  | M |  | H | Monitor all projects testing schedule to analysis the impacts of a delay to the other projects and take required actions to minimize the impacts. | Escalate any issues causing delays to remediate quickly and minimize the impacts to other projects.
Risk that delays in acquiring the infrastructure components for the non-Prod environments may impact the testing schedule |  | H |  | H | Multifonds Release 4.0 and Pre-Release 4.1 testing will be performed on a vendor hosted test environment |  | Assumption to be proven | Impact of Assumpti being incorrect
[7 empty] | Test Resources will be available to start at the beginning of the scheduled testing activities and be assigned through to the end of testing activities for each project | Delay testing schedule.
Risk that a high number of vendor defects and/or extended defect turnaround time may impact testing schedule |  | M |  | H | Monitor Vendor’s defect tracking systems on a regular basis for defect resolution updates | Escalate any delays in defect resolution that will impact the testing schedule
5.2 Dependencies
[7 empty] | One Portfolio QA will be resourced to manage the test effort on all projects | Possible inconsisten between projects an potential lo of any testi synergies
o
Dependency between | Potential Impact of Dependency |  | Owners
Test case creation is | Delay the

## Table 15
Assumption to be proven |  | Impact of Assumption being incorrect |  | Owners
between projects
5.4 Constraints
Constraint on | Impact Constraint has on test effort |  | Owners
Production Support Issues | Delay testing schedule.

## Table 16
6 Sign-off – version 1.3 I have confirmed that the planned Test Strategy described in this document will meet the required needs and addresses any potential risks. The level and types of testing to be completed will be satisfactory in ensuring the required functionality works as per defined requirements. I agree with the test approach identified by the test expert assigned to this work. Approvals o This document was prepared by: Larry Folmes, Portfolio QA This document was also distributed to the following people for review: Jay Sanders, Program Manager Donna Emek, Portfolio Analyst Dean Turman, Portfolio Architect Jolene Klajncar, Development Lead |  | Kirandeep Bagha, Business Analyst Rhonda Sandberg, Business Analyst Ismael Mukhtar, Business SME/Tester Scott Hunter, Business SME/Tester Murray Hutchinson, Business SME/Tester Lindy Naturkach, Business SME/Tester Kendra Pries, Business SME/Tester Guy Carriere, Business SME/Tester Rajdeep Mahal, Quality Assurance Analyst Integration Project: Pervaiz, Aftab, Project Manager Marcela Sussi, Systems Analyst Scott Cochrane, Systems Analyst Marina Ferguson, Systems Analyst Doris Wiebe, Systems Analyst Gurmukh Roopra, Systems Analyst George Poritsanos, Systems Analyst
Joe Brekelmans Account Manager, Investment Systems Date :
FW Final IAS Program Definition D Chris Zaplitny Vice-President IFR / SFFS Date :
Infrastructure Project: Adam Conci, Project Manager Susan Zuk, Systems Architect Tim Hellsten, Infrastructure Specialist Darin Paterson, Infrastructure Specialist Peter Schreibmaier, Infrastructure Specialist Bojana Boticki, Infrastructure Specialist Core Implementation Project: Guillaume De Meyer, Project Manager (Multifonds) Joel Will, Business Project Manager Glen Marttila, Business Project Manager – SFFS John Bettencourt, Business QA/Test Lead Ashley Verot, Assistant Manager, SFFS Surya Goel, Business Analyst Jason Chaikosky, Business Analyst | Kristen Hokke, Systems Analyst Jay Bauerlein, Software Developer Dean Norrie, Software Developer Delvin Klimack, Software Developer Mark Fleck, Software Developer Devadev Annadurai, Software Developer Sivaramakrish na Thondapi, Software
Developer Lalit Tankala, Software Developer Ihor Hluszok, Senior Systems Architect Alex Wiebe, Systems Architect Dean Bartlett, Quality Assurance Analyst Sreya Chakravarty, Quality Assurance Analyst IRFI Gap Closure Project: Mary Coghlin, Project Manager Lynda Hughes, Lead Analyst Terri Sinclair, Lead Developer Donna Coombs, Business SME/Tester Tonia Montoya, Business SME/Tester Internal Audit: Ken Fanstone, AVP Internal Audit Wade Bo-Maguire, Manager, Internal Audit Systems Sushma Uniyal, Associate Mgr, Internal Audit Systems Karyn Masson, Associate Audit Manager Laura Wetton, Assistant Audit Manager

## Table 17
Appendix A: Testing Checklists Security Application Security Standard This standard outlines how software applications must adequately protect the use and management of the Enterprise’s information. The controls within this standard apply to all new project initiatives, whether they are interactive or batch in nature and regardless of their ownership (business vs infrastructure) or design (in-house built vs purchased).
Application Security Standard |  | Applied? |  |  | COMMENTS
|  | Yes | No | N/A
Standards for Testing
1 | All software must be comprehensively tested prior to being placed into production, by persons other than the designers/developers of the system.
2 | All data must be scrubbed to remove any personally-identifiable information before begin used in test environments |  |  |  | Production data will be used for testing but no personal information is included. Approval to use production data for testing has been obtained in the Investment Accounting System (IAS) Program – Testing Framework document.
3 | All code must be subjected to a peer review to assist in identifying potential security weaknesses.
4 | Applications which expose client/corporate confidential data or which have a high sensitivity to breaches of confidentiality, integrity or availability must be tested for application-layer vulnerabilities.
5 | Tests including expected and actual results must be formally documented and any defects must be tracked and resolved.

## Table 18
1 800-665-2410 Hearing Impaired Line: (204) 985- 8832 Declaration of Guarantor for Proof of Identity Please print in black or blue ink and print this form single-sided. |  | Driver’s Licence Identification Card
Applicant’s Information (must be completed in the presence of the guarantor)
Legal Surname: Row | Legal Given Name(s): Danny
Physical Address (no PO Box #s): 72 Donald | Apt. #:
City, Town or Village: winnipeg | Postal Code: R3C1L7
Date of Birth: (mm/dd/yyyy) 1960/02/02 Manitoba Drivers Licence Number CH-AK-RP-K151P4
I certify that I am the individual named above, and that my date of birth and residential address are as stated above, and the signature below is my signature. I consent to Manitoba Public Insurance collecting the information about me set out under the Applicant’s Information section from my guarantor and such other personal information about me from my guarantor or other third parties as necessary to verify my eligibility for the driver’s licence or identification card.
If Applicant under 18 years of age Applicant’s Signature Legal Guardian(s) Signature:
Choosing an Eligible Guarantor
Your guarantor must: 1. Be a Canadian citizen residing in Canada 2. Have known you for at least two years 3. Meet the occupation or offices criteria exactly as described 4. Fully complete the Declaration of Guarantor section on the reverse side of this document WARNING to all applicants and guarantors – Any false statement, misrepresentation or concealment of any material fact on this form, or on any other document presented in support of this application, may be grounds for criminal prosecution. The personal information contained in this form is collected under the authority of section 12 or 150.5 of The Drivers and Vehicles Act and under the authority of section 36(b) (information relates directly and is necessary for a program operated by Manitoba Public Insurance) of The Freedom of Information and Protection of Privacy Act. The personal information is used to administer the driver’s licence or identification card records. If you have any questions about the collection of your personal information, please contact the Manitoba Public Insurance Contact Centre at (204) 985-7000.
Declaration of Guarantor (must be fully completed)
Surname: Given Name: Name of Firm/Organization: Official Title: Business Telephone: Home Telephone: Business Address: Knowledge of Applicant (# of Years): *IMPORTANT* You must have at least TWO years knowledge of the applicant to be an eligible guarantor.

## Table 19
Investment Accounting System (IAS) Program – SFFS Test Strategy v1.3
Place a check mark beside the applicable occupation or office and provide the additional information if requested
| 1. Dentist* | 18. Teacher of a primary or secondary school: School Division School Name 19. Professional Accountant – CPA 20. Professional Engineer 21. Senior administrator of a university or community college: University or college name 22. Teacher at a university or community college: University or college name 23. Veterinarian* 24. Chief of a band, as defined in the Indian Act (Canada): Name of First Nation, Tribal Council or Community 25. Membership clerk of a band, as defined in the Indian Act (Canada): Name of First Nation, Tribal Council or Community 26. Member of Parliament 27. Member of the Legislative Assembly or Provincial Parliament of another province or territory of Canada 28. Federal penitentiary warden: Name of Institution 29. Social Worker* 30. Nurse practitioner* 31. Parole Officer Employer Name 32. Probation Officer 33. Corrections Officer – Name of Institution
2. Medical Doctor*
3. Chiropractor*
4. Judge
5. Justice of the Peace
6. Royal Canadian Mounted Police Officer: Unit Name Detachment Badge #
7. Provincial / Municipal Police Force Officer: Unit Name Detachment Badge #
8. Military Police Officer: Unit Name Detachment Badge #
9. Military Commanding Officer: Unit Name Detachment Badge #
10. Lawyer*
11. Mayor, reeve or other chief elected official of municipality: City/ Municipality
12. Minister of religion authorized under the laws of Manitoba to perform marriages or authorized to do so under the laws of another province or territory in Canada: Name of Religious Organization
13. Notary Public
14. Optometrist
15. Pharmacist*: Licence #
16. Postmaster - as designated by the Canada Post Corporation Act
17. Principal of a primary or secondary school: School Division School Name
*(Must be registered or licensed in Canada)

## Table 20
Investment Accounting System (IAS) Program – SFFS Test Strategy v1.3
I declare that I am actively employed or engaged in Canada in the occupation or office indicated above, and that I am a Canadian citizen. To the best of my knowledge and belief, all of the statements made in this application are true, and the signature shown is a true representation of the applicant’s signature. I have known the applicant for at least TWO years. I authorize Manitoba Public Insurance to take such steps as it considers necessary to verify my authority to act as a qualified guarantor, and to collect my personal information for that purpose. I authorize my employer, my professional association, or my governing body (as the case may be) to disclose such personal information to Manitoba Public Insurance as is necessary to confirm my qualification to act as a guarantor. Guarantor’s Signature: Date: Signed at (City/Province):