## Table 1
Great-West Life Information Services
Investment Accounting System (IAS) - Segregated Funds Financial Services (SFFS) Test Strategy
Version 1.3 March 26, 2014
Confidential Multicompany, 2020 Page 1
Document Revision History
Document Location: \\Gwlanfs8\ias program\Testing\Establish Test Strategy and Plan
Version | Date | Author/Editor | Comments
0.1 | February 28, 2013 | Larry Folmes | Initial version of this document.
0.2 | March 19, 2013 | Larry Folmes | Feedback from D. Emek & J. Bettencourt
1 | March 26, 2013 | Larry Folmes | Feedback from General Review
1.1 | June 28, 2013 | Larry Folmes | Updated to align to revised Project Plan
1.2 | February 12, 2014 | Larry Folmes | Updated to reflect the revised Testing Scope and Project Plan
1.3 | March 26, 2013 | Larry Folmes | Feedback from General Review and revised project schedule
 2003 by GLI, Canada All rights reserved. No part of this publication may be reproduced or transmitted in any form or by any means, electronic or mechanical including photography, recording or any information storage or retrieval system without permission in writing from the publisher. Printed in Canada Template Version: 1.1.1 Template Name: Test Strategy-V1.0 Template Version Date (mm/dd/yy): 10/18/07

## Table 2
Table of Contents TABLE OF CONTENTS 3 1 INTRODUCTION 4 1.1 PURPOSE 4 1.2 PROJECT CONTEXT AND BACKGROUND 4 1.3 SCOPE 5 1.4 DOCUMENT TERMINOLOGY AND ACRONYMS 9 1.5 REFERENCES 10 1.6 TEST OBJECTIVES 10 1.7 TEST MOTIVATORS 11 2 TEST APPROACH 13 2.1 STANDARD QUALITY PROCEDURES & GUIDELINES 13 2.2 CONDUCTING TESTS 13 2.2.1 Unit Testing 13 2.2.2 Functional Testing 14 2.2.3 System Integration Test 14 2.2.4 Regression Testing 15 2.2.5 End-to-End System Testing (Cycle Test) 15 2.2.6 Parallel Testing (Model Office) 16 2.2.7 User Acceptance Testing 16 2.2.8 Security Testing 16 2.3 TEST DELIVERABLES - SFFS 17 2.4 HIGH LEVEL TEST SCHEDULE 18 3 ENVIRONMENTAL NEEDS 21 3.1 BASE SYSTEM HARDWARE 21 3.2 BASE SYSTEM SOFTWARE 22 3.3 TEST ENVIRONMENT CONFIGURATION 22 3.4 TOOLS 23 4 BUSINESS ACCEPTANCE CRITERIA 24 4.1 ACCEPTANCE TEST STRATEGY 24 5 RISKS, DEPENDENCIES, ASSUMPTIONS, AND CONSTRAINTS 25
5.1 | RISKS | 25
5.2 | DEPENDENCIES | 25
5.3 | ASSUMPTIONS | 26
5.4 | CONSTRAINTS | 26
6 SIGN-OFF – VERSION 1.3 27 APPENDIX A: TESTING CHECKLISTS 29
1 Introduction 1.1 Purpose
The purpose of the Test Strategy document for the Investment Accounting System (IAS) Program - SFFS is:  To define a Test Strategy that will guide the project’s testing deliverables through to completion of the SFFS implementation in 2014.  To outline the testing approach, test objectives, scope and the different types of test execution phases that will be used.  To identify the target test items, test environments, test tools, test case structure and defect management process.  To build a common understanding and agreement amongst testing participants and approval from stakeholders.  To ensure that all functionality and changes introduced into the system are compliant and accurate based on the Business requirements and system specifications 1.2 Project Context and Background
MPower, an investment accounting system provided by CGI, is currently used by the GWL segregated fund and general fund back offices; and IG and Mackenzie mutual fund back offices (the “Stakeholders”). The MPower replacement project became a requirement when CGI indicated that they will soon phase out MPower in favor of their new product – Mvest. The change from MPower to MVest is viewed by the Stakeholders to be so significant that it is a system replacement, not simply a system upgrade. Since the Stakeholders are faced with a mandatory system replacement, they have taken the opportunity to evaluate multiple investment accounting system vendors to see which system will best meet the needs of our organization. There was a desire by all Stakeholders to identify a single solution that met all Stakeholders’ needs and provided the best solution from a Power Financial Corp. standpoint. The Stakeholders have undertaken a formal and rigorous process to identify the replacement system that best meets their business needs from a strategic, financial, operational and technological perspective. After an extensive and rigorous process which included RFI and RFP stages, a period of test driving the potential systems, performance tests by vendors and information obtained from industry consultants, GWL identified Multifonds (MF) as the vendor with the best fit for the GWL segregated fund and general account back offices and launched a Concept of Operations as the final round of diligence before requesting and obtaining C-Level approval to proceed with the implementation of a new Investment Accounting System. The Investment Accounting System (IAS) program – SFFS Business Unit implementation will include the following projects:  Core product implementation  Integration – Core Product  Infrastructure  IRFI Gap Closure The IAS Core Implementation Project for SFFS is responsible for functionally configuring the Multifonds Fund Accounting application, converting data from the legacy systems (MPower5 and SF01) into the Multifonds
system, decommissioning the legacy systems and transitioning the business from legacy processes to the future-state processes. The IAS Integration Project is responsible for replacing existing interfaces from MPower5 and SF01 to the new Multifonds solution and, where required, developing new interfaces. Some current interfaces may no longer be required and there may become a need for transitional interfaces required only in the short-term to support successful implementation of the Multifonds solution. The Investment Accounting System (IAS) Infrastructure Project is responsible for putting in place the hardware, software, storage and network components that will support the new IAS solution. It is also responsible for preparing the IS organization to support the new solution and successfully transitioning the infrastructure to production and maintaining that infrastructure until the close-out of the IAS Program at which time it will be transitioned to business as usual (BAU). The IAS IRFI Gap Closure Project is responsible for filling any gap created as a result of the decommissioning of the SF01 System. 1.3 Scope
There will be three testing phases for the Investment Accounting System (IAS) – SFFS. The following initiatives will be part of the testing effort for each testing phase:  Phase 1 – Configuration o Infrastructure Testing – Non-Production Environments  Configuration testing of the new Non-production environments by the Infrastructure Team will include:  Hardware  Operating System  Database  Network  Authorization  Authentication  Security Testing  Infrastructure Vulnerability Assessment Scan o Multifonds Fund Accounting – Release 4.0 Configuration  System Configuration  System Configuration/Setup will be created by the vendor in conjunction with the Business for the following: o Accounting Charts o Security Types (GTI’s) o Operation Codes o NAV Codes o Fee Codes o Currency Codes o Industry Codes o Tax Tables o Valuation Model
o Country Codes o Market Codes (ie New York Stock Exchange) o Workflow and Exemption Monitor (WEM set up)  Application Parameters  Setup validation  Security Groups o Multifonds Fund Accounting – Release 4.0 Configuration Functional  Transaction focused testing of all security types to validate the system configuration meets the Business requirements  Security Testing  Application Vulnerability Assessment Scan  Phase 2 – Functional Core/Gap Closure o Multifonds Fund Accounting – Release 4.1 – Functional Gaps  GWL Functional Gaps  DEV40 - Mutual Fund Trading  DEV63 - Asset Allocation Processing  DEV56 - Peer Groups Exception Management  DEV23 - Fund of Fund Rate of Return Analysis  DEV65 – Automated Distribution Reinvestment  DEV64 - Daily Payable Expense  DEV68 – WEM Control – Identify Deleted NAV Confirmations  DEV51 - User Defined Fields and User Defined Comments  DEV09 - Multi-book Accounting  DEV62 – Fund ROR and Starting Unit Value  DEV48 - Rating Agency Management  DEV72 - Check on Duplicate Trades  DEV71 - Control on Closed Series  DEV70 – Control on Large Security or Shareholder Transaction  DEV69 – NAV Reporting o Multifonds Fund Accounting - Release 4.1 – Security Pricing & WEM  Security Pricing  Inject Price Files  Price Scrubbing / Levels  Foreign Fair Value  Market Value Validation  Price Rollover  WEM – Workflow Exception Management  WEM Configuration  Test WEM Controls  WEM HSM o Multifonds Fund Accounting – Release 4.1 – NAV Cycle  Full Functional test of the NAV Cycle  Start of Day (SOD)  Final (FNL)  End of Day (EOD)  Milestone – To determine if additional performance testing of the Multifonds Fund Accounting application running on the GWL environments is required  Phase 3 – Integration/Reports/Migration/Model Office
o Integration Testing – Functional  SFFS Interfaces  Test planning/execution of SFFS interfaces throughout the agile development cycle  Demand Service - TBD o Security Request Process  Security Master Info  XIP FO to: SS&CNet, Expertus, Solium

## Table 3
 Inbound o Market Data (Pricing)  Pre NAV/PU End of Day Process  Security Prices  Foreign Exchange Rates  Dividend Announcements
o SS&CNet  Trade Capture Process  Trade Info
o Expertus  Trade Capture Process  Trade Info
o Solium  Trade Capture Process (Possible Manual Load – TBD)  Trade Info
o XIP FO  Trade Capture Process  Trade Info  Security Master Info
o CTI |  Pre NAV/PU End of Day Process  Transactions
o MLS  Pre NAV/PU End of Day Process  Transactions
o Optimus  Pre NAV/PU End of Day Process  Transactions
o FundServ  Trade Capture Process  Trade Info
 Outbound o CS15/SAP  NAV End of Day Process  Transactions
o InfoBase  Post NAV/PU End of Day Process  Security Positions  GL Balances  Security Master info  Transactions – Security Trades  Fund/Series Values  Security Prices
o XIP FO  Start of Day Process  Security Positions
 GL Balances (includes Cash) o IC – FO
 Start of Day Process  Security Positions  GL Balances o SS&C Recon (BO and FO)  Start of Day Process  Security Positions  GL Balances – Cash Positions
o GRDB  Post NAV/PU End of Day Process  Security Positions  Security Master info
o Solium  Post NAV/PU End of Day Process (May NOT be required TBD)  Security Positions o SS&C Recon (BO and Custodian)  Post NAV/PU End of Day Process  Security Positions  GL Balances – Cash Positions  Cash Transactions o Internal/External Parties  Post NAV/PU End of Day Process  Fund/Series Values o TAS (Tax Allocation System) o FundServ  Trade Orders  IRFI Interfaces with downstream systems  Inbound o Deposits /Withdrawals Process  Transactions
 Outbound o NAV End of Day Process (Valuation after Deposits/Withdrawals)  Fund/Series Values o Post NAV/PU End of Day Process (Valuation before Deposits/Withdrawals)  Fund/Series Values o IRFI Functional Enhancements  IRFI Functional Enhancements are required due to the decommissioning of the SF01 system  New IRFI tables/processes to support the move of data/functionality from SF01 to IRFI  All IRFI processes that access the new IRFI tables for the SF01 data  New functionality to assume SF01 processing – TBD – Scope to be confirmed during Requirements/Analysis phase  Forcing of unit values including maintaining a category force indicator  London Life zero tax factors  Future valuation dates o InfoCentre SFFS
 GWL developed InfoCentre SFFS Reports/Extracts/Views o Data Migration/Conversion  Test the migration and reconciliation of funds including all hierarchical dependencies. Start by migrating simple funds, moving to larger scale funds; investigating/fixing/improving from one run to another until a full volume test is achieved. o Cycle Test – Functional Integration Test  Cycle Test Detail Test Planning  Functional/Integration testing of all inbound and outbound SFFS interfaces  Data Flow and Data Integrity test from Source Systems, Core and Downstream systems  Validate the correct interfaces are created with the correct data content for each of the 3 daily NAV cycles  Validation of the interfaces files by the Downstream systems o Infrastructure Testing – Production Environment  Configuration testing of the new Production environment by the Infrastructure Team will include:  Hardware  Operating System  Database  Network  Authorization  Authentication  Disaster Recovery (DR) Test  Security Testing  Infrastructure Vulnerability Assessment Scan o Model Office  Parallel Test – Scope TBD during detail test planning  Performance Timing Tests  Load of D/W’s from IRFI  Processing of Available Cash for DEV40 trades (FundSERV, ASL, MSL)  End of Day (EOD) NAV including end to end WEM  Final Security Testing  Infrastructure and Application Vulnerability Assessment Scan Note:  Scope items may change during the year due to Business and Project priorities. 1.4 Document Terminology and Acronyms
The following is a list of acronyms used in this document:
 AD – Application Delivery  BA – Business Analyst  BAU – Business As Usual  BRD – Business Requirements Document  ETL – Extract, Transform and Load  FIT – Functional Integration Testing  GRDB – Global Reporting DataBase  IAS – Investment Accounting System  PM – Project Manager  QA – Quality Assurance  SAN – Systems Analyst  SD - Software Developer  SFFS - Segregated Funds Financial Services  TAS – Tax Allocation System  UAT – User Acceptance Testing 1.5 References
The following is a list of deliverables that will be used as input or otherwise referenced in the development of this document. Project Documents:  Investment Accounting System (IAS) Program – Testing Framework: \\Gwlanfs8\ias program\Testing\Establish Test Strategy and Plan  Investment Accounting System (IAS) Program – Standard Quality Procedures & Guidelines: \\Gwlanfs8\ias program\Testing\Establish Test Strategy and Plan  All RFP Business Requirements Documents are located within the following Folder: \\Gwlanfs8\ias program\99 RFP Work Stream\RFP Business Requirements Analysis and High Level Design  All Gap BRD are located on the SharePoint Site - SEG-Net :  All Integration Requirements Documents are located within the following Folder: \\Gwlanfs8\ias program\30 Integration Project\30.2 Integration Blueprint 1.6 Test Objectives
The general objective of testing is to verify that the system solution meets the stated Business requirements. The specific objectives for each test level are defined below:

## Table 4
| Test Level | Responsibility | Objective
| Unit Test | Development Teams / Vendor |  To verify each software unit executes according to design specifications, and that it is free of data and logic errors.
| Functional Test | Test Team |  To verify the Multifonds Fund Accounting Core Product, Configuration setup/changes, gap closure enhancements, data migration and reports work and process correctly according to Business Requirements.
| System Integration | Test Team |  To verify all system interfaces in the system specifications process correctly with the new application and existing applications  To verify that interdependent modules/systems processes work correctly together after the inclusion of the new application and modified code.
| Regression Test | Test Team |  To verify the existing code continues to process correctly after the integration of the modified code.  Test Team will determine the extent of regression testing to be performed by analyzing the impact the functional change has on the system.
| Non-Functional Test | IS Technical Test Team |  Run automated performance scripts to verify the new application meets the performance requirements.
| End-to-End System Test (Cycle Test) | Test Team |  To verify all system changes, system interfaces and data feeds work correctly together and deliver the expected results.
| Parallel Test (Model Office) | Test Team |  To verify the processing of a number of business process cycles using the same sub-set of data on both the new and old systems; produce the same results.
| Acceptance Test | Business |  To establish business acceptance of the system .changes.  To verify the new application and system changes work correctly and deliver the expected results from the business perspective.
| Security Testing | Testing Services |  To verify there are no critical security vulnerabilities with either the infrastructure assets and/or the application that could compromise the integrity of business processes or allow unauthorized access to secure sensitive data.
1.7 Test Motivators
Validate all functionality and functional enhancements introduced in the new application work correctly according to the Business Requirements and System Specifications. Validate all interfaces/data feeds, user interfaces and ETL processes work correctly and deliver the expected results.
Obtain Business Acceptance of the delivered functionality.

## Table 5
2 Test Approach 2.1 Standard Quality Procedures & Guidelines
The test effort for all three phases of the Investment Accounting System (IAS) Program – SFFS Business Unit implementation will follow the QA procedures as outlined in the Investment Account System (IAS) Program Standard Quality Procedures & Guidelines: IAS Program Standard Test Proced 2.2 Conducting Tests 2.2.1 Unit Testing
Technique Objective: | To validate that each software module executes according to design specifications and is free of any logic defects.
Technique/Strategy: | The GWL development teams will perform unit testing of all changed software modules in their development test environment for the Integration project. The vendor will perform unit and system testing of all Core Product enhancements and bug fixes in their own test environment before being released to GWL
Required Tools:
Success Criteria: | No code will be released to the QA test team until all unit testing has been executed and passed. Failure to perform adequate unit testing will result in increased number of defects, rework time and project delays.
Special Considerations:

## Table 6
2.2.2 Functional Testing
Technique Objective: | To verify the Multifonds Fund Accounting Core Product, configuration setup/changes, gap closure enhancements, data migration and reports work and process correctly according to Business Requirements.
Technique/Strategy: | The QA test team from the Core Implementation project will functionally test the application & code changes for the Core Product, configuration setup/changes, gap closure enhancements, data migration and reports in the GWL test environments. The QA test team from the IRFI Gap Closure project will functionally test the IRFI application & code changes required to fill the gap created by the decommissioning of the SF01 system. Detail Test Plan (s) will contain all planned and reviewed test scenarios and test cases that will be executed for each testing phase.
Required Tools: | ClearQuest will be used as the defect management tool for all systems. Any results which vary from the expected result will be logged as a defect.
Success Criteria: | Successful completion of all planned test cases with no outstanding Severity 1 or 2 defects.
Special Considerations:
2.2.3
on Test
Technique Objective: | To verify all system interfaces in the system specifications process correctly with the new application and existing applications To verify that interdependent modules/systems processes work correctly together after the inclusion of the new application and modified code.
Technique/Strategy: | The QA test team from the Integration project will functionally test all new interfaces from/to the Core Product and validate the data flow from/to the existing applications in the GWL test environments.
Required Tools: | ClearQuest will be used as the defect management tool for all systems. Any results which vary from the expected result will be logged as a defect.
Success Criteria: | Successful completion of all planned test cases with no outstanding Severity 1 or 2 defects.
Special Considerations:

## Table 7
2.2.4 Regression Testing
Technique Objective: | To verify the existing code continues to process correctly after the integration of the modified code.
Technique/Strategy: | Regression testing will be combined with the functional/integration testing performed by the QA Test Team (s). The QA Test Team (s) will determine the extent of regression testing to be performed by analyzing the impact of the functional change to ensure the existing code (after the integration of the modified code) continues to work correctly and deliver the expected results. The analysis of the impact of the functional change will include the SAN, SD and BA if required.
Required Tools: | ClearQuest will be used as the defect management tool for all systems. Any results which vary from the expected result will be logged as a defect.
Success Criteria: | Successful completion of all planned test cases with No outstanding Severity 1 or 2 defects.
Special Considerations:
2.2.5 End-to-End System Testing (Cycle Test)
Technique Objective: | To verify all system changes, system interfaces and data feeds work correctly together and deliver the expected results.
Technique/Strategy: | A series of Business process cycles will be executed to validate the Core product, all system changes, system interfaces and data feeds work correctly together. The process will test data migration, SF processing, workflow/procedures, daily reconciliation, reporting and inbound/outbound interfaces to validate processing from the core application to the existing applications. The QA test teams from the Core Implementation, IRFI Gap Closure and Integration projects will be involved in the test planning and test execution of the End-to-End testing.
Required Tools: | ClearQuest will be used as the defect management tool for all systems. Any results which vary from the expected result will be logged as a defect.
Success Criteria: | Successful completion of all planned test cases with No outstanding Severity 1 or 2 defects.
Special Considerations:

## Table 8
2.2.6 Parallel Testing (Model Office)
Technique Objective: | To verify the processing of a number of business process cycles using the same sub-set of data on both the new and old systems; produce the same results.
Technique/Strategy: | A series of Business process cycles will be executed on the same subset of data on both the new and old systems. Test results will be validated on both the new and old systems to verify the same results are obtained.
Required Tools: | ClearQuest will be used as the defect management tool for all systems. Any results which vary from the expected result will be logged as a defect.
Success Criteria: | Successful completion of all planned test cases with No outstanding Severity 1 or 2 defects.
Special Considerations:
2.2.7 User Acceptance Testing
Technique Objective: | To establish business acceptance of the solution and verify the solution works correctly and delivers the expected results from the business perspective.
Technique/Strategy: | User Acceptance Testing (UAT) will be performed by the Business. The Business will review and approve all the completed detail test plans and test results from all the functional and system integration testing performed through the three phases of the SFFS implementation. The End-to-End and Parallel testing will be the final part of the User Acceptance Testing. End-to-End and Parallel (UAT) test plans will be created/executed by the Business and contain all the test scenarios/cases (test sets/conditions) required to be executed successfully to obtain business acceptance.
Required Tools: | ClearQuest will be used as the defect management tool for all systems. Any results which vary from the expected result will be logged as a defect.
Success Criteria: | Successful completion of all the End-to-End (UAT) planned test cases and approval of all functional and system integration completed test plans and test results.
Special Considerations:
2.2.8 Security Testing

## Table 9
Technique Objective: | To verify there are no critical security vulnerabilities with either the infrastructure assets and/or the application that could compromise the integrity of business processes or allow unauthorized access to secure sensitive data.
Technique/Strategy: | Testing Services will run Vulnerability Assessment scans on the infrastructure assets and Core Product application to identify any security vulnerability threats. All critical/severe severity issues for the infrastructure assets and high/medium severity for the application will be reported back to the appropriate project team. The project team will be required to perform the required remediation action and the scan will be rerun.
Required Tools: | Testing Services is responsible for the Vulnerability Assessment scan tools.
Success Criteria: | Once all the identified security issues have been remediated.
Special Considerations:
2.3 Test Deliverables - SFFS  This is a Canada Life Internal Information and should not be shared outside.  Test Strategy - SFFS  Test Deliverables by Test Phase
o Detailed Test Plan (s) – Test Scenarios/Cases (Test Sets/Conditions) o Test Managements Reports  Weekly Dashboard/Status Report  Defect Reports o Completed Detailed Test Plan (s) and Test Results o Test Summary Report

## Table 10
SFFS Test Strategy
Test Phase 1- Configuration
Detail Test Plan (s)
Test Execution (s) – Status / Defect Reports
Completed Detail Test Plan (s) & Results
Phase 1 Test Summary
Test Phase 2 – Functional Core/Gap Closure
Detail Test Plan (s)
Test Execution (s) – Status / Defect Reports
Completed Detail Test Plan (s) & Results
Phase 2 Test Summary
Test Phase 3 – Integration/Reports/ Migration/Model Office
Detail Test Plan (s)
Test Execution (s) – Status / Defect Reports
Completed Detail Test Plan (s) & Results
Phase 3 Test Summary
2.4 High Level Test Schedule
Below is the high-level test schedule for the Investment Accounting System (IAS) Program – SFFS Implementation – Mar 2013 – May 2014.

## Table 11
Test Activity | Mar | Apr | May | Jun | July | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May
Test Strategy - SFFS | Mar: TBD
Phase 1 - Infrastructure | Jun: TBD; July: TBD
Phase 1 – MF Rel 4.0 – Configuration Test Plan | May: TBD
Phase 1 – MF Rel 4.0 – configuration Test Execution | Jun: TBD; July: TBD
Phase 1 – MF Rel 4.0 – Functional Test Planning | Jun: TBD; July: TBD
Phase 1 – MF Rel 4.0 – Functional Test Execution | July: TBD; Aug: TBD
Phase 2 – Rel 4.1 – Dev Test Planning | Aug: TBD; Sep: TBD
Phase 2 – Rel 4.1 – Dev Test Execution | Oct: TBD; Nov: TBD; Dec: TBD; Jan: TBD; Feb: TBD
Phase 2 – Rel 4.1 – Pricing & WEM Test Planning | Nov: TBD
Phase 2 – Rel 4.1 – Pricing & WEM Test Execution | Dec: TBD; Jan: TBD
Phase 2 – Rel 4.1 – NAV Cycle Test Planning | Dec: TBD; Jan: TBD
Phase 2 – Rel 4.1 – NAV Cycle Test Execution | Jan: TBD
Phase 3 – Integration – Testing throughout Agile Development & FIT | July: TBD; Aug: TBD; Sep: TBD; Oct: TBD; Nov: TBD; Dec: TBD; Jan: TBD; Feb: TBD
IRFI System Testing | Aug: TBD; Sep: TBD; Oct: TBD; Nov: TBD
IRFI Integration Testing | Aug: TBD; Sep: TBD; Oct: TBD; Nov: TBD; Dec: TBD
IRFI UAT/End-User Testing | Dec: TBD; Jan: TBD; Feb: TBD; Mar: TBD; Apr: TBD
IRFI Implementation | May: TBD
Info Center Reporting | Jan: TBD; Feb: TBD; Mar: TBD; Apr: TBD; May: TBD
Phase 3 – Data Migration – Test Planning | Feb: TBD
Phase 3 – Data Migration – Test Execution | Mar: TBD; Apr: TBD
Cycle Test – Test Planning | Dec: TBD; Jan: TBD; Feb: TBD
Cycle Test – Test Execution | Feb: TBD; Mar: TBD; Apr: TBD

## Table 12
Phase 3 – Model Office – Test Planning | TBD | TBD
Infrastructure Testing - Prod | TBD | TBD
Phase 3 – Model Office – Test Execution |  | TBD | TBD
Implementation –SFFS |  |  | TBD

## Table 13
3 Environmental Needs 3.1 Base System Hardware
The following table sets forth the system resources for the test effort.
System Resources
Resource | Quantity | Name and Type
Presentation Layer Server | 1 | - GWIASAPU1 (Dev, FIT, UAT & Support) - IBM x3650 M4, 3.46Ghz, dual sockets, single 8 Core CPU - Memory: 96GB - Disk: 146 GB mirrored
Reporting Server | 1 | - GWIASAPU2 (Dev, FIT, UAT & Support) - IBM x3650 M4, 3.46Ghz, dual sockets, single 8 Core CPU - Memory: 96GB - Disk: 146 GB
Presentation Layer Server | 1 | - GWIASAPP1 (Prod) - IBM x3650 M4, 3.46Ghz, dual sockets, single 8 Core CPU - Memory: 96GB - Disk: 146 GB mirrored
Presentation Layer Server | 1 | - GWIASAPP2 (Prod) - IBM x3650 M4, 3.46Ghz, dual sockets, single 8 Core CPU - Memory: 96GB - Disk: 146 GB mirrored
Reporting Server | 1 | - GWIASAPP3 (Prod) - IBM x3650 M4, 3.46Ghz, dual sockets, single 8 Core CPU - Memory: 96GB - Disk: 146 GB
Reporting Server | 1 | - GWIASAPP4 (Prod) - IBM x3650 M4, 3.46Ghz, dual sockets, single 8 Core CPU - Memory: 96GB - Disk: 146 GB
Integration Server | 1 | - Gwetlapd1 or lletlapd1 (dev) - Gwetlapp1 or lletlapp1 (prod) - AIX 6.1 P7
Application/Database Servers | 1 | - DEV - GWIASDBD1 - UAT - GWIASDBU1/2 - FIT – GWIASDBF1 - SUPPORT – GWIASDBT1 - PROD – GWIASDBP1/2 - P770 - AIX 6.1 TL5
Storage |  | - 3TB VMAX - 1 Dedicated Storage Node License

## Table 14
System Resources
Resource | Quantity |  | Name and Type
(UNIX) - 7 Non-Dedicated Storage Nodes for UNIX - VTL space
Central File Share Server | 1 |  | TBD
SQL Transition DB Server | 1 |  | - GWIASDBT1 - Windows VMware Server ESXi 4.1
SQL WEB Server Tool | 1 |  | - GWSFODEVIAS1 - Windows 2003
MOVEIT Central Server | 1 |  | - SFTPPROD03 - Windows VMWare Server ESXi 4.1
MOVEIT DMZ | 1 |  | - SFTPPROD03 - Windows VMWare Server ESXi 4.1
3.2 Base System Software
The following base software elements are required in the test environment for this Test Strategy.
Software Element Name |  | Version |  | Type and Other Notes
Client Tier
Internet Explorer |  | 7 or 8
Windows |  | 7
Java applet |  | SUN JRE 1.6.0_20
Middle Tier – Presentation Server
Windows Server |  | 2008 R2
Weblogic Suite |  | 2010-03-05
Middle Tier – Reporting Server
Business Intelligence Publisher
Weblogic Server Enterprise Edition
Middle Tier – Integration Server
Ab Initio Co>Operating System |  | 3.0.4
Database Server
Oracle Server Database Enterprise Ed |  | 11g R2 11.2.0.3
Oracle Diagnostics Pack
Oracle Partitioning
Multifonds |  | 4
Backup Software (UNIX & Windows) |  |  |  | Networker
Networker Backup Agents |  |  |  | 25 Pack Networker licenses for Windows and UNIX
3.3 Test Environment Configuration
The following Test Environment Configurations needs to be provided and supported for this project.  DEV – Development (DEV1, DEV2)
 FIT – Integration (FIT1)  UAT – User Acceptance (UAT1, UAT2, UAT3, UAT4) 3.4 Tools

## Table 15
The following tools will be used for this project
| Tool | Vendor/In-house
Defect Tracking | Clear Quest | Vendor
Project Management | Primavera | Vendor
4 Business Acceptance Criteria 4.1 Acceptance Test Strategy
The successful execution of the different levels of testing for each test phase will prove that the application can be deployed to Production. UAT (User Acceptance testing) will establish business acceptance of the application and verify the application works correctly and delivers the expected results from the Business perspective. The Business will review and approve the all detailed test plans and test results obtained during the different levels of testing performed by the test team (s) for all three phases. The Model Office Testing will consist of the End-to-End and Parallel Testing. The Model Office testing will be the final part of the User Acceptance Testing. End-to-End and Parallel (UAT) test plans will be created/executed by the Business and contain all the test scenarios/cases (test sets/conditions) needed to be executed to successfully to obtain business acceptance.

## Table 16
5 Risks, Dependencies, Assumptions, and Constraints 5.1 Risks
All project risks are documented and managed at a project/program level. The following risks associated with testing should also be highlighted:
Risk | Probability |  | Impact | Mitigation Strategy | Contingency
Risk that testing resources are not 100% allocated to the projects will impact project schedule | H |  | H | Full time resources internal/external can be requested. Monitor shared resources workload against schedule. | Additional external resources can be engaged to meet project timelines.
Risk that delays encountered in the testing phase of one project may impact the testing schedule of the other projects | M |  | H | Monitor all projects testing schedule to analysis the impacts of a delay to the other projects and take required actions to minimize the impacts. | Escalate any issues causing delays to remediate quickly and minimize the impacts to other projects.
Risk that delays in acquiring the infrastructure components for the non-Prod environments may impact the testing schedule | H |  | H | Multifonds Release 4.0 and Pre-Release 4.1 testing will be performed on a vendor hosted test environment
Risk that a high number of vendor defects and/or extended defect turnaround time may impact testing schedule | M |  | H | Monitor Vendor’s defect tracking systems on a regular basis for defect resolution updates | Escalate any delays in defect resolution that will impact the testing schedule
5.2 Dependencies
Dependency between |  | Potential Impact of Dependency |  |  |  | Owners

## Table 17
Dependency between | Potential Impact of Dependency | Owners
Test case creation is dependent on requirements/specifications being completed on time. | Delay the start of test case creation.
Test execution is dependent on code being written/modified and unit tested by GWL and the vendor respectively | Delay the start of test case execution.
Test execution schedule is based on the vendor’s software release schedule | Any delays in the vendor release schedule will delay the start of test execution for that phase of testing
5.3 Assumptions
Assumption to be proven | Impact of Assumption being incorrect | Owners
Test Resources will be available to start at the beginning of the scheduled testing activities and be assigned through to the end of testing activities for each project | Delay testing schedule.
One Portfolio QA will be resourced to manage the test effort on all projects | Possible inconsistency between projects and potential loss of any testing synergies between projects
5.4 Constraints
Constraint on | Impact Constraint has on test effort | Owners
Production Support Issues | Delay testing schedule.
6 Sign-off – version 1.3 I have confirmed that the planned Test Strategy described in this document will meet the required needs and addresses any potential risks. The level and types of testing to be completed will be satisfactory in ensuring the required functionality works as per defined requirements. I agree with the test approach identified by the test expert assigned to this work. Approvals
Joe Brekelmans Account Manager, Investment Systems Date :
FW Final IAS Program Definition Do Chris Zaplitny Vice-President IFR / SFFS Date :
This document was prepared by: Larry Folmes, Portfolio QA This document was also distributed to the following people for review: Jay Sanders, Program Manager Donna Emek, Portfolio Analyst Dean Turman, Portfolio Architect Jolene Klajncar, Development Lead Infrastructure Project: Adam Conci, Project Manager Susan Zuk, Systems Architect Tim Hellsten, Infrastructure Specialist Darin Paterson, Infrastructure Specialist Peter Schreibmaier, Infrastructure Specialist Bojana Boticki, Infrastructure Specialist Core Implementation Project: Guillaume De Meyer, Project Manager (Multifonds) Joel Will, Business Project Manager Glen Marttila, Business Project Manager – SFFS John Bettencourt, Business QA/Test Lead Ashley Verot, Assistant Manager, SFFS Surya Goel, Business Analyst
Jason Chaikosky, Business Analyst Kirandeep Bagha, Business Analyst Rhonda Sandberg, Business Analyst Ismael Mukhtar, Business SME/Tester Scott Hunter, Business SME/Tester Murray Hutchinson, Business SME/Tester Lindy Naturkach, Business SME/Tester Kendra Pries, Business SME/Tester Guy Carriere, Business SME/Tester Rajdeep Mahal, Quality Assurance Analyst Integration Project: Pervaiz, Aftab, Project Manager Marcela Sussi, Systems Analyst Scott Cochrane, Systems Analyst Marina Ferguson, Systems Analyst Doris Wiebe, Systems Analyst Gurmukh Roopra, Systems Analyst George Poritsanos, Systems Analyst Kristen Hokke, Systems Analyst Jay Bauerlein, Software Developer Dean Norrie, Software Developer Delvin Klimack, Software Developer Mark Fleck, Software Developer Devadev Annadurai, Software Developer Sivaramakrishna Thondapi, Software Developer Lalit Tankala, Software Developer Ihor Hluszok, Senior Systems Architect Alex Wiebe, Systems Architect Dean Bartlett, Quality Assurance Analyst Sreya Chakravarty, Quality Assurance Analyst IRFI Gap Closure Project: Mary Coghlin, Project Manager Lynda Hughes, Lead Analyst Terri Sinclair, Lead Developer Donna Coombs, Business SME/Tester Tonia Montoya, Business SME/Tester Internal Audit: Ken Fanstone, AVP Internal Audit Wade Bo-Maguire, Manager, Internal Audit Systems Sushma Uniyal, Associate Mgr, Internal Audit Systems Karyn Masson, Associate Audit Manager Laura Wetton, Assistant Audit Manager
Appendix A: Testing Checklists Security Application Security Standard This standard outlines how software applications must adequately protect the use and management of the Enterprise’s information. The controls within this standard apply to all new project initiatives, whether they are interactive or batch in nature and regardless of their ownership (business vs infrastructure) or design (in-house built vs purchased).

## Table 18
Application Security Standard |  | Applied? |  |  | COMMENTS
|  | Yes | No | N/A
Standards for Testing
1 | All software must be comprehensively tested prior to being placed into production, by persons other than the designers/developers of the system.
2 | All data must be scrubbed to remove any personally-identifiable information before begin used in test environments |  |  |  | Production data will be used for testing but no personal information is included. Approval to use production data for testing has been obtained in the Investment Accounting System (IAS) Program – Testing Framework document.
3 | All code must be subjected to a peer review to assist in identifying potential security weaknesses.
4 | Applications which expose client/corporate confidential data or which have a high sensitivity to breaches of confidentiality, integrity or availability must be tested for application-layer vulnerabilities.
5 | Tests including expected and actual results must be formally documented and any defects must be tracked and resolved.
REQUEST FOR TEMPORARY OUT-OF-PROVINCE BENEFITS (FOR ABSENCES EXCEEDING THREE MONTHS) DEMANDE DE SERVICES POUR LES PERSONNES RÉSIDANT TEMPORAIREMENT À L’EXTÉRIEUR DE LA PROVINCE (PENDANT PLUS DE TROIS MOIS) Manitoba Health 300 Carlton Street Winnipeg MB R3B 3M9 (204) 786-7101 Fax (204) 783-2171 Toll free 1-800-392-1207 T.D.D. (Hearing Impaired) (204) 774-8618 Confidential Health Care Fraud Line (204) 786-7118 Toll free fax 1-866-608-2983 Web site: Manitoba health registration number: 460333940 www.manitoba.ca Email: insuredben@gov.mb.ca Santé Manitoba 300, rue Carlton Winnipeg MB R3B 3M9 (204) 786-7101 Téléc.: (204) 783-2171 Sans Frais 1-800-392-1207 ATME (Malentendents): (204) 774-8618 Ligne confidentielle de dénonciation - domaine de la santé Téléc. sans frais 1-866-608-2983 Site Web: www.manitoba.ca Courriel: insuredben@gov.mb.ca This form when completed requests out-of-province benefits in accordance with the regulations under The Health Services Insurance Act of Manitoba and, where applicable, pursuant to the Prescription Drug Cost Assistance Act, for the person or persons listed. This request is subject to the approval of Manitoba Health. En vertu des réglements pris en application de la Loi sur l’assurance- maladie et, le cas échéant, de la Loi sur l’aide à l’achat de médicaments sur ordonnance, cette formule, une fois remplie, autorise la ou les personnes dont les noms apparaissent ci-dessous à obtenir des services à l’extérieur de la province. Cette demande est toutefois sujette à l’approbation de Santé Manitoba. Please print Veuillez écrire en lettres moulées Name: Telephone No.: Nom : Nº de téléphone : Present Address: Addresse actuelle : Postal Code: Email: Code Postal : Courriel : Manitoba Health Registration No.: Personal Health ID No.: Nº d’immatriculation à Santé Manitoba : Nº d’identification personnelle : INFORMATION REGARDING TEMPORARY ABSENCE FROM PROVINCE RENSEIGNEMENTS CONCERNANT LES PERSONNES RÉSIDANT TEMPORAIREMENT À L’EXTÉRIEUR DE LA PROVINCE Reason for Request: Raison de la demande : Do you wish to receive a Temporary Out-of-Province Registration Certificate to ensure uninterrupted coverage during your stay outside the province (and limited coverage for out-of country medical and hospital service), or for third party insurance purposes? Yes No Souhaitez-vous recevoir un Certifcat d’immatriculation hors province temporaire afin que votre couverture ne soit pas interrompue pendant votre séjour à l’extérieur de la province (et que vous puissiez bénéficier d’une couverture limitée pour des services médicaux ou hospitaliers à l’extérieur du pays), ou pour des besoins d’assurance de responsabilité civile? Oui Non Do you wish to apply for up to an additional 100 day supply of medications for out-of-country travel? Souhaitez-vous faire une demande pour obtenir jusqu’à 100 jours supplémentaires de médicaments pour la période où vous serez à l’étranger? Yes No (Absence must be outside Canada and greater than 100 days / Oui Non Absence doit être à l’extérieur du Canada et pour une période de plus de 100 jours.) Names of spouse/dependents who will be temporarily absent from Manitoba: Noms du/de la conjoint/e et/ou des personnes à charge qui résideront temporairement à l’extérieur de la province: First Name/Prénom PHIN/NIMP
MH #604 MG-5678 (Rev 04/17) Over/Verso Please check box if spouse/dependants requires up to an additional 100 day supply of medications for out of country travel. Veuillez cocher la case correspondante si le/la conjoint/e ou les personnes à charge ont besoin d’une réserve allant jusqu’à 100 jours supplémentaires de médicaments pour la période où vous serez à l’étranger. Vacation Vacances Employment Emploi Humanitarian Aid Worker Travailleur humanitaire Temporary address outside Manitoba: Adresse temporaire à l’extérieur du Manitoba : Postal Code/Code Postal Telephone No./Nº de téléphone I (We) will be temporarily absent from Manitoba Effective: Nous résiderons temporairement à l’extérieur du Manitoba à partir du : Day/Jour Month/Mois Year/Année I (We) will be returning to Manitoba Effective: Nous serons de retour au Manitoba le : Day/Jour Month/Mois Year/Année I certify that the above information is correct. Je certifie que les renseignements ci-dessus sont exacts. Signature Date FOR MANITOBA HEALTH/ ESPACE RÉSERVÉ À SANTÉ MANITOBA Comments/Remarques : Request approved: Demande approuvée : Yes/Oui No/Non Signature Date “The purpose for which this information is being collected is to enable Manitoba Health to provide you with health coverage and/or service. If you require any further information about the collection of this information, please do not hesitate to contact a Manitoba Health representative at 786- 7101.” “Ces renseignements sont demandés pour permettre à Santé Manitoba de vous offrir des services de santé ou une assurance-maladie. Si vous avez besoin d’autres renseignements au sujet de cette collecte, n’hésitez pas à communiquer avec un représentant de Santé Manitoba au 786-7101.”